## General
ENABLING WORKS - REVIEW COMMENTS SHEET
Aconex Ref: | LUS-XXXXX-CAC-TSS-RCS-XXX-00001 | Organisation | CAC-Technical Support Services
Date of Latest Submittal: | Day Month Year | Plot: | XXXXX |  | Note: All documents must be signed & sealed by the project Design/Supervision Consultant prior to official submittal
Date of Review: | Day Month Year - Review No. X | Attention of: | CAC-TSS Project Manager
Supervision Consultant | XXXXXX | Enabling Works Contractor | XXXXX
Item No | Information Required to be submitted by the Design/Supervision Consultant | Has the document been provided? (For Lusail Use Only) | Supervision Consultant Response on ……….. | Response to Developer Submittal of ……………….. by Lusail on ……………………… | Supervision Consultant Response on ……………………
TECHNICAL ITEMS TO BE REVIEWED BY LUSAIL CAC
1 | Geotechnical Investigation Report Provide geotechnical investigation report for the plot that is based on sufficient number of boreholes.
2 | Boundary, Topographic & Utility Survey Provide a topographic survey of the plot showing boundary lines with coordinates that matches those on the Plot Plan. The survey shall show levels of all visible features, such as road kerbs, entrance driveways, existing utilities, etc. The survey shall extend to adjacent roads and into neighboring property (if accessible). This survey shall also show all existing and/or future visible and underground utilities surrounding the plot whether located inside or outside the plot limit. These utilities shall include, as applicable, but not limited to: Utility Tunnel, Pneumatic Waste, District Cooling, Electrical, QTel, Gas, Potable Water, ELV, Storm Water, Foul Sewer, Irrigation, etc. The issued IFC and or As Built utility drawings shall be used for guidance only. A survey shall be conducted to identify the exact location of all utilities. Hand digging of trial holes/pits is only permitted within the plot limits. Any other underground survey shall be carried out in a non-destructive manner using underground survey equipment. All trial holes/pits shall be reinstated properly. All levels shall be in "m" QNHD.
3 | Utility, Excavation & Shoring Cross-Sections Provide cross-sections at all plot boundaries showing all utilities, plot limits, future structure, excavation limits, slopes and shoring (if any). The cross-sections shall extend from the building/basement wall to the road kerb or beyond the neighbor's property line tying to the existing ground level. These cross-sections shall be accurate and to scale and shall clearly show dimensions, including the distance between utilities (existing & future) and the plot boundary. Special cross-sections shall be taken at each utility structure and at plot access entrance(s) showing all the above mentioned references and road levels. All Levels shall be in "m" QNHD.
4 | Utility Management Method Statement Create a detailed method statement on how each utility is to be managed during the enabling works phase until final connection to the building is made. This shall include all utility structures, house connections, ducts, pipes, valves, etc.
5 | Excavation Plan and Method Statements Provide an excavation plan and detailed method statement that indicates the excavation works will not in any way damage any of the adjacent infrastructure or utilities. If the maximum slopes exceed that recommended by the geotechnical investigation report, a slope stability analysis must be prepared to support and justify the steeper excavation banks; and provide additional calculations to prove that the existing infrastructure will be stable (e.g. not prone to rotation or tilting) and will not undergo undue stresses during and after excavation that could damage the infrastructure or utilities in any way. Also, provide a separate detailed method statement that states how fissures and/or cavities (if encountered) will be treated to ensure that excavation banks are deemed safe.
6 | Shoring System Design and Method Statement Prepare a shoring system design and provide a detailed method statement that also indicates that the construction works will not in any way damage any of the adjacent infrastructure or utilities. Note that the use of vibro hammers for driving and extracting pile casings is strictly prohibited in close proximity to any existing Lusail utility, roadway and landscape/hardscape infrastructure. A computer analysis of the proposed shoring system that supports the system viability shall be provided; along with a computer analysis to indicate the variation in soil deformation outside the plot boundaries both in the horizontal and vertical directions, up to the adjacent road kerbs and 5m into the adjacent plot(s) boundary. A table on the shoring system plans shall be shown for monitoring the deflection scheme during excavation. The Supervision Consultant shall specify the method of monitoring. Note that the maximum allowable deflection shall not exceed 40mm. The monitoring devices/data to be installed/obtained at least 25m apart and shall be monitored at least twice a week as shown on the sample below:
7 | Dewatering System Details Prepare dewatering system design calculations and plan; and provide a method statement for the installation of the dewatering system with a statement that indicates that the dewatering system will not in any way damage the adjacent existing Lusail utility and roadway infrastructure. If a dewatering system is not required, the Consultant shall provide evidence of the present groundwater levels within the plot. In designing the dewatering system, the Consultant shall assume and use a water table level of +1.00m QNHD in the design calculations regardless of the existing/present groundwater levels.
8 | Notes to be Added on All Enabling Work Drawings: a) The ultimate responsibility for safe execution of the proposed Enabling Works in accordance with the project drawings listed in the Design Consultants design certificate and without detriment to any related permanent features in the vicinity of the proposed works rests with the Enabling Works Contractor and his appointed Design Consultant. To be added on all the proposed shoring system drawing(s). b) The Enabling Works Contractor shall continuously measure pile/wall displacements during the works and compare them with the calculated displacements. If at any time the measured displacements exceed the calculated values, the Enabling Works Contractor shall immediately inform the Supervision Consultant, investigate the reasons and take appropriate remedial measures to ensure that the calculated displacements are not exceeded during the works. To be added on all proposed shoring system drawing(s). c) The proposed dewatering system as shown on the drawings and as designed shall be available to be installed as soon as the ground water levels dictate. To be added on all proposed dewatering system drawing(s). d) The proposed works (temporary or permanent) shall not encroach beyond the authorised plot limits. e) All elevations are referenced to QNHD
ADDITIONAL SUPPORT DOCUMENTS REQUIRED (IF APPLICABLE)
9 | Plot Plan Provide a copy of the Plot Plan that was provided by Lusail as a part of the Sales and Purchase Agreement
10 | Insurance Certificates Provide copies of Supervision Consultant (PI) and Enabling Works Contractor (All Risk) valid insurance certificates.
11 | Construction Programme Provide Supervision Consultant signed and sealed copy of the Construction Programme from enabling works to final completion (Level 2 only)
12 | Waterproofing System Provide details of the waterproofing system for the permanent works.
ITEMS THAT LUSAIL CAC WILL FORWARD TO LUSAIL HSSELQ DEPARTMENT (LOGISTICS) FOR REVIEW AND APPROVAL. THE SUPERVISION CONSULTANT/ ENABLING WORKS CONTRACTOR SHALL FOLLOW UP JOINTLY WITH LUSAIL HSSELQ DEPARTMENT (LOGISTICS) TO OBTAIN APPROVED COPY AND INCLUDE IN THE NEXT SUBMITTAL TO LUSAIL CAC
13 | HSE Plan Provide an HSE plan endorsed by the Supervision Consultant for review and approval of Lusail HSSELQ
14 | Site Logistics Plan Provide a copy of the construction logistics drawing showing site offices, signage, labour welfare facilities, temporary water tank, temporary generator, fuel tank, laydown area, material storage, vehicular access, etc. Note that all site mobilization facilities shall be shown to be located within the plot limits. If additional space is required outside the plot limit, in advance to Lusail CAC submittal, the Supervision Consultant & Enabling Works Contractor shall approach and coordinate with Lusail Building Application Coordinator and Lusail Logistics to determine the availability and duration of neigboring space to be shown on the Site Logistics Plan. Subsequent to Lusail CAC submittal of the Site Logistics Plan, the Supervision Consultant/Enabling Works Contractor shall follow up with Lusail Logistics to obtain their approval, and an approved copy shall be provided to Lusail CAC for their record.
15 | Signboard & Hoarding Fence Plan Provide main signboard and hoarding fence plans to Lusail CAC (in accordance with Lusail standards) for Lusail Logistics review and approval.
ITEMS TO BE OBTAINED BY THE SUPERVISION CONSULTANT FROM LUSAIL LOGISTICS AND A SIGNED COPY TO BE PROVIDED TO LUSAIL CAC
16 | Dewatering Discharge Point Provide a copy of the dewatering discharge point plan to Lusail CAC which has been coordinated and approved by Lusail Logistics
17 | Site Access Route Access routes through Lusail for construction traffic to be coordinated with Logistics AFTER LCAC have provided an NOC for the enabling works. A copy of the Lusail Logistics approved plan shall be provided to LCAC for their record.
ACTION BY SUPERVISION CONSULTANT/ENABLING WORKS CONTRACTOR PRIOR TO MOBILIZATION
18 | LCAC Pre-mobilization Photographic Site Report The Developer's Supervision Consultant shall arrange for a joint site visit with LCAC upon mobilization after which LCAC will issue a report. If this process is not initiated by the Developer’s Supervision Consultant, LCAC will then consider that the Developer/Supervision Consultant/Enabling Works Contractor is accepting Lusail's existing roadway, utility, and landscape/hardscape infrastructure surrounding the plot in perfect condition prior to mobilization.